|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Activities** | | **Total duration**  **(number of weeks)** | **M1** | **M2** | **M3** | **M4** | **M5** | **M6** | **M7** | **M8** | **M9** | **M10** | **M11** | **M12** |
| **Ref.nr/**  **Sub-ref**  **nr** | **Title** |
| 1.1. | National departments on relations with employers (RED) | **1** | **1X** |  |  |  |  |  |  |  |  |  |  |  |
| 1.2. | Kick-off meeting | **1** | **1=** |  |  |  |  |  |  |  |  |  |  |  |
| 1.3. | List of participating organizations | **5** |  | **3X** | **2X** |  |  |  |  |  |  |  |  |  |
| 1.4. | List of criteria for employability system (ES) analysis | **2** |  |  | **2X** |  |  |  |  |  |  |  |  |  |
| 1.5. | Benchmarking of “university-employers” relations in EU and CA countries | **8** |  |  |  | **4=X** | **4X** |  |  |  |  |  |  |  |
| 2.1. | Draft version of guidelines on “University-Employer” cooperation | **4** |  |  |  |  |  | **4X** |  |  |  |  |  |  |
| 2.2. | Workshop | **1** |  |  |  |  |  |  | **1=** |  |  |  |  |  |
| 2.3. | Final version of guidelines | **4** |  |  |  |  |  |  | **3X** | **1X** |  |  |  |  |
| 2.4. | Guidelines publishing | **1** |  |  |  |  |  |  |  | **1X** |  |  |  |  |
| 3.1. | UENC work plan | **6** |  |  |  |  |  |  |  | **2X** | **4X** |  |  |  |
| 3.2. | Staff for UENCs | **2** |  |  |  |  |  |  |  |  | **2=** |  |  |  |
| 3.3. | Validation of UENCs by Ministries | **12** |  |  |  |  |  |  |  |  |  | **4X** | **4X** | **4X** |
| 3.4. | CA Network of UENCs | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1. | Requirements specification | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2. | Database of employers and potential employees | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3. | UENC Portal for career finding | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.4. | UENC Portal deployment | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.5. | Portal guidelines | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1. | CA UAA | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2. | Training of Alumni Associations leaders in EU | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3. | Annual plan of events for students by UAA | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.4. | Registration of UAA as NGO | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.5. | Annual conference of Ministries with UAA | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1. | Project promotion by UAA | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2. | New employers involvement by UENC | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.3. | National Job Fairs by UENC | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.4. | Poll of UENC Portal users and job fairs participants | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.5. | Report on needed improvement and current progress of UENC Portal | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 7.1. | Project web-site | **48** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** |
| 7.2. | Promotion in mass-media | **2** |  |  | **1X** |  |  |  |  |  | **1X** |  |  |  |
| 7.3. | Publishing materials on project activities | **6** |  |  |  |  |  |  | **3X** |  |  |  |  | **3X** |
| 7.4. | Annual conferences | **1** |  |  |  |  |  |  |  |  |  |  | **1=** |  |
| 7.5. | Recommendations on ES improvement | **2** |  |  |  |  |  | **2=** |  |  |  |  |  |  |
| 8.1. | Quality Control Commission (QCC) | **2** | **2=X** |  |  |  |  |  |  |  |  |  |  |  |
| 8.2. | Internal semi-annual evaluation of the project | **4** |  |  |  |  |  | **4X** |  |  |  |  |  |  |
| 8.3. | Analytical reports on UE relations changes | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 8.4. | Annual experts' review | **3** |  |  |  |  |  |  |  |  |  |  |  | **3=** |
| 9.1. | General and Local Project Management Group | **4** | **2=** | **2X** |  |  |  |  |  |  |  |  |  |  |
| 9.2. | Day-to-day management | **48** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** |
| 9.3. | Project documentation keeping and analysing | **48** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** |
| 9.4. | Quarterly reports on project progress and implementation of activities | **8** |  |  | **2=X** |  |  | **2=X** |  |  | **2=X** |  |  | **2=X** |
| 9.5. | Coordination meetings | **1** |  |  |  |  |  |  | **1=** |  |  |  |  |  |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Activities** | | **Total duration**  **(number of weeks)** | **M1** | **M2** | **M3** | **M4** | **M5** | **M6** | **M7** | **M8** | **M9** | **M10** | **M11** | **M12** |
| **Ref.nr/**  **Sub-ref**  **nr** | **Title** |
| 1.1. | National departments on relations with employers (RED) | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2. | Kick-off meeting | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3. | List of participating organizations | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4. | List of criteria for employability system (ES) analysis | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5. | Benchmarking of “university-employers” relations in EU and CA countries | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1. | Draft version of guidelines on “University-Employer” cooperation | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2. | Workshop | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3. | Final version of guidelines | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4. | Guidelines publishing | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1. | UENC work plan | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2. | Staff for UENCs | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3. | Validation of UENCs by Ministries | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4. | CA Network of UENCs | **4** | **4X** |  |  |  |  |  |  |  |  |  |  |  |
| 4.1. | Requirements specification | **12** |  |  | **4=X** | **4X** | **4X** |  |  |  |  |  |  |  |
| 4.2. | Database of employers and potential employees | **12** |  |  |  |  |  | **4X** | **4X** | **4X** |  |  |  |  |
| 4.3. | UENC Portal for career finding | **20** |  |  |  |  |  |  |  | **4X** | **4X** | **4X** | **4X** | **4X** |
| 4.4. | UENC Portal deployment | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.5. | Portal guidelines | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1. | CA UAA | **4** | **4X** |  |  |  |  |  |  |  |  |  |  |  |
| 5.2. | Training of Alumni Associations leaders in EU | **2** |  | **2=** |  |  |  |  |  |  |  |  |  |  |
| 5.3. | Annual plan of events for students by UAA | **8** |  |  | **4X** | **4X** |  |  |  |  |  |  |  |  |
| 5.4. | Registration of UAA as NGO | **12** |  |  |  |  | **4X** | **4X** | **4X** |  |  |  |  |  |
| 5.5. | Annual conference of Ministries with UAA | **1** |  |  |  |  |  |  |  |  |  |  | **1X** |  |
| 6.1. | Project promotion by UAA | **10** |  |  |  |  |  |  |  | **2X** | **2X** | **2X** | **2X** | **2X** |
| 6.2. | New employers involvement by UENC | **10** |  |  |  | **2X** | **1X** | **1X** | **1X** | **1X** | **1X** | **1X** | **1X** | **1X** |
| 6.3. | National Job Fairs by UENC | **4** |  |  |  |  |  | **2X** | **2X** |  |  |  |  |  |
| 6.4. | Poll of UENC Portal users and job fairs participants | **2** |  |  |  |  |  |  |  |  | **2X** |  |  |  |
| 6.5. | Report on needed improvement and current progress of UENC Portal | **1** |  |  |  |  |  |  |  |  |  | **1X** |  |  |
| 7.1. | Project web-site | **48** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** |
| 7.2. | Promotion in mass-media | **2** |  |  | **1X** |  |  |  |  |  | **1X** |  |  |  |
| 7.3. | Publishing materials on project activities | **6** |  |  |  | **3X** |  |  |  | **3X** |  |  |  |  |
| 7.4. | Annual conferences | **1** |  |  |  |  |  |  |  |  |  |  | **1=** |  |
| 7.5. | Recommendations on ES improvement | **2** | **2=** |  |  |  |  |  |  |  |  |  |  |  |
| 8.1. | Quality Control Commission (QCC) | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 8.2. | Internal semi-annual evaluation of the project | **4** |  |  |  |  |  | **4X** |  |  |  |  |  |  |
| 8.3. | Analytical reports on UE relations changes | **2** |  |  |  |  | **2X** |  |  |  |  |  |  |  |
| 8.4. | Annual experts' review | **3** |  |  |  |  |  |  |  |  |  |  |  | **3=** |
| 9.1. | General and Local Project Management Group | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.2. | Day-to-day management | **48** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** |
| 9.3. | Project documentation keeping and analysing | **48** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** |
| 9.4. | Quarterly reports on project progress and implementation of activities | **8** |  |  | **2=X** |  |  | **2=X** |  |  | **2=X** |  |  | **2=X** |
| 9.5. | Coordination meetings | **1** |  |  |  |  |  |  | **1=** |  |  |  |  |  |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Activities** | | **Total duration**  **(number of weeks)** | **M1** | **M2** | **M3** | **M4** | **M5** | **M6** | **M7** | **M8** | **M9** | **M10** | **M11** | **M12** |
| **Ref.nr/**  **Sub-ref**  **nr** | **Title** |
| 1.1. | National departments on relations with employers (RED) | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2. | Kick-off meeting | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3. | List of participating organizations | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4. | List of criteria for employability system (ES) analysis | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.5. | Benchmarking of “university-employers” relations in EU and CA countries | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1. | Draft version of guidelines on “University-Employer” cooperation | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2. | Workshop | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3. | Final version of guidelines | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.4. | Guidelines publishing | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1. | UENC work plan | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2. | Staff for UENCs | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3. | Validation of UENCs by Ministries | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4. | CA Network of UENCs | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1. | Requirements specification | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2. | Database of employers and potential employees | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3. | UENC Portal for career finding | **12** | **4X** | **4X** | **4X** |  |  |  |  |  |  |  |  |  |
| 4.4. | UENC Portal deployment | **16** |  |  |  |  |  |  |  |  | **4X** | **4X** | **4X** | **4X** |
| 4.5. | Portal guidelines | **4** |  |  | **1X** | **3X** |  |  |  |  |  |  |  |  |
| 5.1. | CA UAA | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2. | Training of Alumni Associations leaders in EU | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3. | Annual plan of events for students by UAA | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.4. | Registration of UAA as NGO | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.5. | Annual conference of Ministries with UAA | **1** |  |  |  |  |  |  |  |  |  |  | **1X** |  |
| 6.1. | Project promotion by UAA | **24** | **2X** | **2X** | **2X** | **2X** | **2X** | **2X** | **2X** | **2X** | **2X** | **2X** | **2X** | **2X** |
| 6.2. | New employers involvement by UENC | **12** | **1X** | **1X** | **1X** | **1X** | **1X** | **1X** | **1X** | **1X** | **1X** | **1X** | **1X** | **1X** |
| 6.3. | National Job Fairs by UENC | **4** |  |  |  |  |  | **2X** | **2X** |  |  |  |  |  |
| 6.4. | Poll of UENC Portal users and job fairs participants | **8** |  |  |  | **2X** | **2X** |  |  |  | **2X** | **2X** |  |  |
| 6.5. | Report on needed improvement and current progress of UENC Portal | **2** |  |  |  |  |  | **1X** |  |  |  |  | **1X** |  |
| 7.1. | Project web-site | **48** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** | **4X** |
| 7.2. | Promotion in mass-media | **2** |  |  | **1X** |  |  |  |  |  | **1X** |  |  |  |
| 7.3. | Publishing materials on project activities | **6** |  |  |  | **3X** |  |  |  |  |  |  |  | **3X** |
| 7.4. | Annual conferences | **1** |  |  |  |  |  |  |  |  |  |  | **1=** |  |
| 7.5. | Recommendations on ES improvement | **2** |  |  |  |  | **2=** |  |  |  |  |  |  |  |
| 8.1. | Quality Control Commission (QCC) | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 8.2. | Internal semi-annual evaluation of the project | **4** |  |  |  |  |  | **4X** |  |  |  |  |  |  |
| 8.3. | Analytical reports on UE relations changes | **4** |  |  |  |  |  |  | **2X** |  |  |  |  | **2X** |
| 8.4. | Annual experts' review | **3** |  |  |  |  |  |  |  |  |  |  |  | **3=** |
| 9.1. | General and Local Project Management Group | **0** |  |  |  |  |  |  |  |  |  |  |  |  |
| 9.2. | Day-to-day management | **48** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** |
| 9.3. | Project documentation keeping and analysing | **48** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** | **4=X** |
| 9.4. | Quarterly reports on project progress and implementation of activities | **8** |  |  | **2=X** |  |  | **2=X** |  |  | **2=X** |  |  | **2=X** |
| 9.5. | Coordination meetings | **1** |  |  |  |  |  |  | **1=** |  |  |  |  |  |