## Partners
No | Partners | Country | Type | INFO | Mandate
P1 | University of Patras | Greece | UNI / coordinator |  | +
P2 | Bath Spa University | United Kingdom | UNI / EU | + | +
P3 | Link Campus University | Italy | UNI / EU | + | +
P4 | Koblenz-Landau University | Germany | UNI / EU | + | +
P5 | Stiching Network University | Netherlands | UNI / EU | + | +
P6 | Tashkent State Technical University | Uzbekistan | UNI / CA | + | +
P7 | Karshi State University | Uzbekistan | UNI / CA |  | +
P8 | Association of Employers | Uzbekistan | ASSOTIATION | + | +
P9 | Ministry of Education | Uzbekistan | MINISTRY |  | +
P10 | Kyrgyz State Technical University | Kyrgyzstan | UNI | + | +
P11 | BAFE | Kyrgyzstan | UNI | + | +
P12 | Osh Technological University | Kyrgyzstan | UNI | + | +
P13 | Bishkek Business Club | Kyrgyzstan | ASSOTIATION | + | +
P14 | Ministry of Education | Kyrgyzstan | MINISTRY | + | +
P15 | Khujand State University | Tajikistan | UNI | + | +
P16 | Khorog State University | Tajikistan | UNI | + | +
P17 | Tajik Pedagogical University | Tajikistan | UNI
P18 | Sogd Broadcast Company | Tajikistan | ASSOTIATION |  | +
P19 | Ministry of Education | Tajikistan | MINISTRY
P20 | KIMEP | Kazakhstan | UNI |  | +
P21 | Al-Farabi Kazakhstan National University | Kazakhstan | UNI |  | +
P22 | Association of high-tech energy eff. & innovative companies | Kazakhstan | ASSOTIATION
P23 | Academy of Pedagogy | Kazakhstan | ASSOTIATION
P24 | Ministry of Education and Science | Kazakhstan | MINISTRY

## Skeleton
| Preparation | Description
WP1 | Benchmarking of “university-employers” relations for CA countries
1.1. | National departments on relations with employers (RED)
1.2. | Kick-off meeting
1.3. | List of participating organizations
1.4. | List of criteria for employability system (ES) analysis
1.5. | Benchmarking of “university-employers” relations in EU and CA countries
Development
WP2 | Guidelines for National Centers
2.1. | Draft version of guidelines on “University-Employer” cooperation
2.2. | Workshop
2.3. | Final version of guidelines
2.4. | Guidelines publishing
Development
WP3 | "Universities-Employers" National Centres (UENC)
3.1. | UENC workplan
3.2. | Staff for UENCs
3.3. | Validation of UENCs by Ministries
3.4. | CA Network of UENCs
Development
WP4 | Development of UENC Portal
4.1. | Requirements specification
4.2. | Database of employers and potentional employees
4.3. | UENC Portal for career finding
4.4. | UENC Portal deployment
4.5. | Portal guidelines
Development
WP5 | University Alumni Associations (UAA)
5.1. | CA UAA
5.2. | Training of Alumni Associations leaders in EU
5.3. | Annual plan of events for students by UAA
5.4. | Registration of UAA as NGO
5.5. | Annual conference of Ministries with UAA
Dissemination & exploitation
WP6 | National Job Fairs
6.1. | Project promotion by UAA
6.2. | New employers involvement by UENC
6.3. | National Job Fairs by UENC
6.4. | Poll of UENC Portal users and job fairs participants
6.5. | Report on needed improvement and current progress of UENC Portal
Dissemination & exploitation
WP7 | Dissemination
7.1. | Project web-site
7.2. | Promotion in mass-media
7.3. | Publishing materials on project activities
7.4. | Annual conferences
7.5. | Recommendations on ES improvement
Quality plan
WP8 | Quality control and monitoring
8.1. | Quality Control Commision (QCC)
8.2. | Internal semi-annual evaluation of the project
8.3. | Analytical reports on UE relations changes
8.4. | Annual experts' review
Management
WP9 | Management of the project
9.1. | General and Local Project Management Group
9.2. | Day-to-day management
9.3. | Project documentation keeping and analysing
9.4. | Quarterly reports on project progress and implementation of activities
9.5. | Coordination meetings

## Workplan
Activities |  | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Total duration (number of weeks) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
№ | Title
1.1. | National departments on relations with employers (RED) | 1 | [12 empty] | 0 | [12 empty] | 0 | bar: M1
1.2. | Kick-off meeting | 1 | [12 empty] | 0 | [12 empty] | 0 | bar: M1
1.3. | List of participating organizations | 5 | [12 empty] | 0 | [12 empty] | 0 | bar: M2 to M3
1.4. | List of criteria for employability system (ES) analysis | 2 | [12 empty] | 0 | [12 empty] | 0 | bar: M3
1.5. | Benchmarking of “university-employers” relations in EU and CA countries | 8 | M4: 4X=; M5: 4X | 0 | [12 empty] | 0
2.1. | Draft version of guidelineson “University-Employer” cooperation | 4 | [12 empty] | 0 | [12 empty] | 0 | bar: M6
2.2. | Workshop | 1 | [12 empty] | 0 | [12 empty] | 0 | bar: M7
2.3. | Final version of guidelines | 4 | [12 empty] | 0 | [12 empty] | 0 | bar: M7 to M8
2.4. | Guidelines publishing | 1 | [12 empty] | 0 | [12 empty] | 0 | bar: M8
3.1. | UENC workplan | 6 | [12 empty] | 0 | [12 empty] | 0 | bar: M8 to M9
3.2. | Staff for UENCs | 2 | [12 empty] | 0 | [12 empty] | 0 | bar: M9
3.3. | Validation of UENCs by Ministries | 12 | [12 empty] | 0 | [12 empty] | 0 | bar: M10 to M12
3.4. | CA Network of UENCs | 0 | [12 empty] | 4 | 4X | [11 empty] | 0
4.1. | Requirements specification | 0 | [12 empty] | 12 |  |  | 4X | 4X | 4X | [7 empty] | 0
4.2. | Database of employers and potentional employees | 0 | [12 empty] | 12 | [5 empty] | 4X | 4X | 4X |  |  |  |  | 0
4.3. | UENC Portal for career finding | 0 | [12 empty] | 20 | [7 empty] | 4X | 4X | 4X | 4X | 4X | 12 | 4X | 4X | 4X
4.4. | UENC Portal deployment | 0 | [12 empty] | 0 | [12 empty] | 16 | [8 empty] | 4X | 4X | 4X | 4X
4.5. | Portal guidelines | 0 | [12 empty] | 0 | [12 empty] | 4 |  |  | 1X | 3X
5.1. | CA UAA | 0 | [12 empty] | 4 | 4X | [11 empty] | 0
5.2. | Training of Alumni Associations leaders in EU | 0 | [12 empty] | 2 |  | 2= | [10 empty] | 0
5.3. | Annual plan of events for students by UAA | 0 | [12 empty] | 8 |  |  | 4X | 4X | [8 empty] | 0
5.4. | Registration of UAA as NGO | 0 | [12 empty] | 12 |  |  |  |  | 4X | 4X | 4X | [5 empty] | 0
5.5. | Annual conference of Ministries with UAA | 0 | [12 empty] | 1 | [10 empty] | 1X |  | 1 | [10 empty] | 1X
6.1. | Project promotion by UAA | 0 | [12 empty] | 10 | [7 empty] | 2X | 2X | 2X | 2X | 2X | 24 | 2X | 2X | 2X | 2X | 2X | 2X | 2X | 2X | 2X | 2X | 2X | 2X
6.2. | New employers involvement by UENC | 0 | [12 empty] | 10 |  |  |  | 2X | 1X | 1X | 1X | 1X | 1X | 1X | 1X | 1X | 12 | 1X | 1X | 1X | 1X | 1X | 1X | 1X | 1X | 1X | 1X | 1X | 1X
6.3. | National Job Fairs by UENC | 0 | [12 empty] | 4 | [5 empty] | 2X | 2X | [5 empty] | 4 | [5 empty] | 2X | 2X
6.4. | Poll of UENC Portal users and job fairs participants | 0 | [12 empty] | 2 | [8 empty] | 2X |  |  |  | 8 |  |  |  | 2X | 2X |  |  |  | 2X | 2X
6.5. | Report on needed improvement and current progress of UENC Portal | 0 | [12 empty] | 1 | [9 empty] | 1X |  |  | 2 | [5 empty] | 1X |  |  |  |  | 1X
7.1. | Project web-site | 48 | [12 empty] | 48 | 4X | 4X | 4X | 4X | 4X | 4X | 4X | 4X | 4X | 4X | 4X | 4X | 48 | 4X | 4X | 4X | 4X | 4X | 4X | 4X | 4X | 4X | 4X | 4X | 4X | bar: M1 to M12
7.2. | Promotion in mass-media | 2 | [12 empty] | 2 |  |  | 1X | [5 empty] | 1X |  |  |  | 2 |  |  | 1X | [5 empty] | 1X | bar: M3; M9
7.3. | Publishing materials on project activities | 6 | [12 empty] | 6 |  |  |  | 3X |  |  |  | 3X |  |  |  |  | 6 |  |  |  | 3X | [7 empty] | 3X | bar: M7; M12
7.4. | Annual conferences | 1 | [12 empty] | 1 | [10 empty] | 1= |  | 1 | [10 empty] | 1= | bar: M11
7.5. | Recommendations on ES improvement | 2 | [12 empty] | 2 | 2= | [11 empty] | 2 |  |  |  |  | 2= | bar: M6
8.1. | Quality Control Commision (QCC) | 2 | M1: 2=X | 0 | [12 empty] | 0
8.2. | Internal semi-annual evaluation of the project | 4 | [12 empty] | 4 | [5 empty] | 4X | [6 empty] | 4 | [5 empty] | 4X | bar: M6
8.3. | Analytical reports on UE relations changes | 0 | [12 empty] | 2 |  |  |  |  | 2X | [7 empty] | 4 | [6 empty] | 2X |  |  |  |  | 2X
8.4. | Annual experts' review | 3 | [12 empty] | 3 | [11 empty] | 3= | 3 | [11 empty] | 3=X | bar: M12
9.1. | General and Local Project Management Group | 4 | [12 empty] | 0 | [12 empty] | 0 | bar: M1 to M2
9.2. | Day-to-day management | 48 | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 48 | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 48 | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X
9.3. | Project documentation keeping and analysing | 48 | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 48 | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 48 | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X
9.4. | Quarterly reports on project progress and implementation of activities | 8 | M3: 2=X; M6: 2=X; M9: 2=X; M12: 2=X | 8 |  |  | 2=X |  |  | 2=X |  |  | 2=X |  |  | 2=X | 8 |  |  | 2=X |  |  | 2=X |  |  | 2=X |  |  | 2=X
9.5. | Coordination meetings | 1 | [12 empty] | 1 | [6 empty] | 1= | [5 empty] | 1 | [6 empty] | 1= | bar: M7

## Staff-costs-days
|  | P1 |  |  |  | P2 |  |  |  | P3 |  |  |  | P4 |  |  |  | P5 |  |  |  | P6 |  |  |  | P7 |  |  |  | P8 |  |  |  | P9 |  |  |  | P10 |  |  |  | P11 |  |  |  | P12 |  |  |  | P13 |  |  |  | P14 |  |  |  | P15 |  |  |  | P16 |  |  |  | P17 |  |  |  | P18 |  |  |  | P19 |  |  |  | P20 |  |  |  | P21 |  |  |  | P22 |  |  |  | P23 |  |  |  | P24
|  | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A | M | R | T | A
1.1. | National departments on relations with employers (RED) | P6 M: 5; P6 A: 5; P7 M: 5; P7 A: 5; P10 M: 5; P10 A: 5; P11 M: 5; P11 A: 5; P12 M: 5; P12 A: 5; P15 M: 5; P15 A: 5; P16 M: 5; P16 A: 5; P17 M: 5; P17 A: 5; P20 M: 5; P20 A: 5; P21 M: 5; P21 A: 5
1.2. | Kick-off meeting | P1 M: 30; P1 A: 30
1.3. | List of participating organizations | P6 M: 10; P6 A: 20; P7 M: 10; P7 A: 20; P10 M: 10; P10 A: 20; P11 M: 10; P11 A: 20; P12 M: 10; P12 A: 20; P15 M: 10; P15 A: 20; P16 M: 10; P16 A: 20; P17 M: 10; P17 A: 20; P20 M: 10; P20 A: 20; P21 M: 10; P21 A: 20
1.4. | List of criteria for employability system (ES) analysis | P7 R: 10; P8 R: 10; P11 R: 10; P13 R: 10; P16 R: 10; P18 R: 10; P21 R: 10; P22 R: 10; P23 R: 10
1.5. | Benchmarking of “UE” relations in EU and CA countries | P2 R: 15; P4 R: 15; P6 R: 20; P8 R: 10; P10 R: 20; P13 R: 10; P15 R: 20; P18 R: 10; P20 R: 20; P22 R: 10; P23 R: 10
2.1. | Draft version of guidelineson “University-Employer” cooperation | P5 M: 5; P5 R: 5; P7 R: 20; P12 R: 20; P17 R: 20; P21 R: 20
2.2. | Workshop | P3 M: 21; P3 A: 21
2.3. | Final version of guidelines | P5 M: 5; P5 R: 5; P7 M: 10; P7 R: 15; P12 M: 10; P12 R: 15; P17 M: 10; P17 R: 15; P21 M: 10; P21 R: 15
2.4. | Guidelines publishing | P7 M: 15; P12 M: 15; P17 M: 15; P21 M: 15
3.1. | UENC workplan | P1 M: 30; P6 M: 25; P11 M: 25; P15 M: 25; P20 M: 25
3.2. | Staff for UENCs | P2 M: 20; P2 R: 20; P2 A: 20
3.3. | Validation of UENCs by Ministries
3.4. | CA Network of UENCs | P6 M: 10; P7 M: 10; P10 M: 10; P11 M: 10; P12 M: 10; P15 M: 10; P16 M: 10; P17 M: 10; P20 M: 10; P21 M: 10
4.1. | Requirements specification | P4 M: 30; P10 M: 30
4.2. | Database of employers and potentional employees | P12 M: 10; P12 R: 30
4.3. | UENC Portal for career finding | P10 R: 20; P10 T: 150
4.4. | UENC Portal deployment | P10 R: 10; P10 T: 40
4.5. | Portal guidelines | P10 R: 20
5.1. | CA UAA
5.2. | Training of Alumni Associations leaders in EU | P2 R: 30
5.3. | Annual plan of events for students by UAA
5.4. | Registration of UAA as NGO
5.5. | Annual conference of Ministries with UAA | P6 M: 10; P6 A: 10; P11 M: 10; P11 A: 10; P16 M: 10; P16 A: 10; P20 M: 10; P20 A: 10
6.1. | Project promotion by UAA
6.2. | New employers involvement by UENC | P6 M: 10; P6 A: 20; P7 M: 10; P7 A: 20; P10 M: 10; P10 A: 20; P11 M: 10; P11 A: 20; P12 M: 10; P12 A: 20; P15 M: 10; P15 A: 20; P16 M: 10; P16 A: 20; P17 M: 10; P17 A: 20; P20 M: 10; P20 A: 20; P21 M: 10; P21 A: 20
6.3. | National Job Fairs by UENC | P6 M: 50; P7 M: 50; P10 M: 50; P11 M: 50; P12 M: 50; P15 M: 50; P16 M: 50; P17 M: 50; P20 M: 50; P21 M: 50
6.4. | Poll of UENC Portal users and job fairs participants | P2 M: 20; P12 A: 20
6.5. | Report on needed improvement and current progress of UENC Portal | P12 M: 15
7.1. | Project web-site | P4 M: 50; P21 R: 50; P21 T: 120
7.2. | Promotion in mass-media
7.3. | Publishing materials on project activities | P1 M: 50; P5 M: 25; P6 M: 50; P11 M: 50; P17 M: 50; P20 M: 50
7.4. | Annual conferences | P1 M: 20; P1 A: 20; P3 M: 20; P3 A: 20; P4 M: 20; P4 A: 20
7.5. | Recommendations on ES improvement | P1 R: 30; P3 R: 30; P5 R: 30
8.1. | Quality Control Commision (QCC)
8.2. | Internal semi-annual evaluation of the project | P7 M: 20; P7 R: 40; P11 M: 10; P11 R: 20; P12 M: 10; P12 R: 20; P15 M: 10; P15 R: 20; P16 M: 10; P16 R: 20; P20 M: 20; P20 R: 40
8.3. | Analytical reports on UE relations changes | P6 R: 30; P11 R: 30; P15 R: 10; P16 R: 20; P20 R: 30
8.4. | Annual experts' review | P1 R: 30; P1 A: 20; P5 R: 30; P5 A: 20
9.1. | General and Local Project Management Group
9.2. | Day-to-day management | P1 M: 240; P1 A: 240; P2 M: 240; P2 A: 240; P3 M: 240; P3 A: 240; P4 M: 240; P4 A: 240; P5 M: 240; P5 A: 240; P6 M: 240; P6 A: 240; P7 M: 240; P7 A: 240; P10 M: 240; P10 A: 240; P11 M: 240; P11 A: 240; P12 M: 240; P12 A: 240; P15 M: 240; P15 A: 240; P16 M: 240; P16 A: 240; P17 M: 240; P17 A: 240; P20 M: 240; P20 A: 240; P21 M: 240; P21 A: 240
9.3. | Project documentation keeping and analysing | P1 M: 120; P1 A: 120; P2 M: 60; P2 A: 60; P3 M: 60; P3 A: 60; P4 M: 60; P4 A: 60; P5 M: 60; P5 A: 60; P6 M: 60; P6 A: 60; P7 M: 60; P7 A: 60; P10 M: 60; P10 A: 60; P11 M: 60; P11 A: 60; P12 M: 60; P12 A: 60; P15 M: 60; P15 A: 60; P16 M: 60; P16 A: 60; P17 M: 60; P17 A: 60; P20 M: 60; P20 A: 60; P21 M: 60; P21 A: 60
9.4. | Quarterly reports on project progress | P1 R: 60; P2 R: 30; P5 R: 30; P7 R: 30; P15 R: 20; P16 R: 20; P20 R: 30
9.5. | Coordination meetings | P1 M: 20; P1 A: 20; P2 M: 20; P2 A: 20; P3 M: 20; P3 A: 20
UNI / coordinator
UNI / EU
UNI / CA
Organization
Ministry

## Travel costs
ST
|  | 1.2. | 2.2. | 3.2. | 4.1. | 5.2. | B | 5.5.-2 | 5.5.-3 | 7.4.-1 | 7.4.-2 | 7.4.-3 | 9.5.-1 | 9.5.-2 | 9.5.-3 |  | UNI / coordinator
P1 | Departure | X |  | Z |  | Z | Z | Z | Z |  |  | X |  |  | X |  | UNI / EU
| Arrival | X |  | Z |  | Z | Z | Z | Z |  |  | X |  |  | X |  | UNI / CA
| Staff/Student | X | 14 | Z | 7 | Z | Z | Z | Z | 4 | 4 | X | 6 | 6 | X |  | Organization
P2 | Departure |  | Z | X |  | X | Z | Z | Z |  |  |  |  | X |  |  | Ministry
| Arrival |  | Z | X |  | X | Z | Z | Z |  |  |  |  | X
| Staff/Student | 14 | Z | X | 7 | X | Z | Z | Z | 2 | 2 | 2 | 6 | X | 6 | X | Принимающий город
P3 | Departure |  | X | Z |  | Z | Z | Z | Z | X | [5 empty] | Z | Не участвует
| Arrival |  | X | Z |  | Z | Z | Z | Z | X | [5 empty] | ST | Students
| Staff/Student | 14 | X | Z | 7 | Z | Z | Z | Z | X | 2 | 2 | 6 | 6 | 6
P4 | Departure |  | Z | Z | X | Z | Z | Z | Z |  | X
| Arrival |  | Z | Z | X | Z | Z | Z | Z |  | X
| Staff/Student | 14 | Z | Z | X | Z | Z | Z | Z | 2 | X | 2 | 6 | 6 | 6
P5 | Departure |  |  | Z | Z | Z | Z | Z | Z |  |  |  | X
| Arrival |  |  | Z | Z | Z | Z | Z | Z |  |  |  | X
| Staff/Student | 14 | 14 | Z | Z | Z | Z | Z | Z | 2 | 2 | 2 | X | 6 | 6
P6 | Departure |  | Z |  |  |  | X | X | X
| Arrival |  | Z |  |  |  | X | X | X
| Staff/Student | 14 | Z | 14 | 7 | 14 | X | X | X | 2 | 2 | 2 | 6 | 6 | 6
P7 | Departure
Arrival
| Staff/Student | 14 | 21 | 14 | 7 | 14 | 4 | 4 | 4 | 2 | 2 | 2 | 6 | 6 | 6
P8 | Departure |  |  | Z | Z | Z | Z | Z | Z
| Arrival |  |  | Z | Z | Z | Z | Z | Z
| Staff/Student | 7 | 7 | Z | Z | Z | Z | Z | Z | 2 | 2 | 2 | 3 | 3 | 3
P9 | Departure |  | Z | Z | Z | Z | X | X | X
| Arrival |  | Z | Z | Z | Z | X | X | X
| Staff/Student | 7 | Z | Z | Z | Z | X | X | X | 2 | 2 | 2 | 3 | 3 | 3
P10 | Departure |  | Z
| Arrival |  | Z
| Staff/Student | 14 | Z | 14 | 14 | 14 | 4 | 4 | 4 | 2 | 2 | 2 | 6 | 6 | 6
P11 | Departure |  | Z |  |  |  | X | X | X
| Arrival |  | Z |  |  |  | X | X | X
| Staff/Student | 14 | Z | 14 | 7 | 14 | X | X | X | 2 | 2 | 2 | 6 | 6 | 6
P12 | Departure
Arrival
| Staff/Student | 14 | 21 | 14 | 7 | 14 | 4 | 4 | 4 | 2 | 2 | 2 | 6 | 6 | 6
P13 | Departure |  |  | Z | Z | Z | Z | Z | Z
| Arrival |  |  | Z | Z | Z | Z | Z | Z
| Staff/Student | 7 | 7 | Z | Z | Z | Z | Z | Z | 2 | 2 | 2 | 3 | 3 | 3
P14 | Departure |  | Z | Z | Z | Z | X | X | X
| Arrival |  | Z | Z | Z | Z | X | X | X
| Staff/Student | 7 | Z | Z | Z | Z | X | X | X | 2 | 2 | 2 | 3 | 3 | 3
P15 | Departure |  | Z
| Arrival |  | Z
| Staff/Student | 14 | Z | 14 | 7 | 14 | 4 | 4 | 4 | 2 | 2 | 2 | 6 | 6 | 6
P16 | Departure |  | Z |  |  |  | X | X | X
| Arrival |  | Z |  |  |  | X | X | X
| Staff/Student | 14 | Z | 14 | 7 | 14 | X | X | X | 2 | 2 | 1 | 6 | 6 | 6
P17 | Departure
Arrival
| Staff/Student | 14 | 21 | 14 | 7 | 14 | 4 | 4 | 4 | 2 | 2 | 2 | 6 | 6 | 6
P18 | Departure |  |  | Z | Z | Z | Z | Z | Z
| Arrival |  |  | Z | Z | Z | Z | Z | Z
| Staff/Student | 7 | 7 | Z | Z | Z | Z | Z | Z | 2 | 2 | 2 | 3 | 3 | 3
P19 | Departure |  | Z | Z | Z | Z | X | X | X
| Arrival |  | Z | Z | Z | Z | X | X | X
| Staff/Student | 7 | Z | Z | Z | Z | X | X | X | 2 | 2 | 2 | 3 | 3 | 3
P20 | Departure |  | Z |  |  |  | X | X | X
| Arrival |  | Z |  |  |  | X | X | X
| Staff/Student | 14 | Z | 14 | 7 | 14 | X | X | X | 2 | 2 | 2 | 6 | 6 | 6
P21 | Departure
Arrival
| Staff/Student | 14 | 21 | 14 | 7 | 14 | 4 | 4 | 4 | 2 | 2 | 2 | 6 | 6 | 6
P22 | Departure |  |  | Z | Z | Z | Z | Z | Z
| Arrival |  |  | Z | Z | Z | Z | Z | Z
| Staff/Student | 7 | 7 | Z | Z | Z | Z | Z | Z | 2 | 2 | 2 | 3 | 3 | 3
P23 | Departure |  |  | Z | Z | Z | Z | Z | Z
| Arrival |  |  | Z | Z | Z | Z | Z | Z
| Staff/Student | 7 | 7 | Z | Z | Z | Z | Z | Z | 2 | 2 | 2 | 3 | 3 | 3
P24 | Departure |  | Z | Z | Z | Z
| Arrival |  | Z | Z | Z | Z
| Staff/Student | 7 | Z | Z | Z | Z | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3

## Equipment costs
1.1. | reds
3.1. | uenc