## Workplan
|  |  |  | New workplan | New description | TEMPUS | Weeks | Date - Start | Date - Finish | Lead organization | Participating organizations | Description | Budget
1. | PREPARATION | Background Analysis and Preparation of National Concept of University-Employers Cooperation |  |  | During workpackage execution International Academic Committee will be established. Deep analysis of situation of existing contacts between the universities and employers and education Quality Assurance will be carried out. EU experience in the particular fields of establishing relations between a university and employers will be generalized. General plans of improving situation and creating network of "university-employers" centres will be elaborated. |  |  | 2015-10-15 | 2016-01-07 | P1 | Ukraine: NMU Poland: WTU Germany: UKOLD Lithuenia: ASU Greece: PU Austria: WUS Ukraine: DCEO, DIA, DESDR, KNU, SSU, CCSG Republic of Belarus: BSU, LSPCMCEC, BrSU, AUB, MEB Armenia: NPUA, ASUE, YSULS, EIF, MEA | Analysis of the situation of the cooperation between universities and employers. The Program of cooperation between universities and employers development will be elaborated. |  |  | NO STAFF COSTS FOR MINISTRIES!!!
1.1. |  |  | Establishment of a NationalAcademic Employment Committee | Bachground analysis of education Quality Assurance (National analysis, preparing information on EU countries and partner experience) | Deep analysis of situation of existing contacts between the universities and employers in different NIS countries and in different fields of economics. Advanced needs' analysis. Generalization of EU experience in the particular fields of establishing relations between universities and employers. |  | 8 |  | 2015-12-10 | NMU |  | Establishment of a national committee which will study the conditions of university-employers relationships | Each non-coordinator institution will send one representative to Koblenz (P1).Two administrators from UKOLD (P1) will be responsible for organization of the event.
1.2. |  |  | Training of National Administration staff of the Regional Coordination Centers | Organization of a International Academic Employment Committee | Establishment of the International Academic Committee responsible for the Regional coordination centers conception development at all participating universities.. Определить сферу деятельности, разработка методических реккомендаций Textbook, на основании его будет переобучаться персонал |  | 4 |  | 2016-01-07 |  |  | Training of national administration staff of the centres regarding university-employers relations. | 3 researchers from P7, P11, P13, P18 PCs take part in analyzes at their native countries. | +
|  |  |  | Design and development of conceptual framework of formation the quality standards of education | Development of Committee's quality standart of education and its approval by all consortium members.
2. | DEVELOPMENT | Regional Coordination Centres for University-Employers Cooperation | [5 empty] | 2016-01-08 | 2018-10-14 |  |  | During workpackage realization, plans of centres’ development will be prepared. It will be prepared Centres’ offices at each university and purchased equipment for them. For Centers' service each of universities will select 3 administrative staff. KLU will organize 2 seminars on management for retraining Centres' administrative staff of 8 NIS partner universities. SMSUH, CSU, NMU will organize seminar for other NIS partner universities for discussion and selection of operative plans of each Centre, prepared during retraining of Centers' staff at EU universities. Each NIS university will make an official opening of the Centres with participation of the employment centers and regional administrations.
2.1. |  |  | Methodological materials and regulations for the centres | Project of concept of University-Employers Cooperation | Establishment by the International Academic Committee of local workgroups at all participating NIS universities, which are responsible for development of corresponding Centre and selection of Centre’s staff. Preparation by the workgroups plans of centres’ development. Consideration and approval of the plans by the International Academic Committee. Наполнение концепции, мобильность, встречи |  | 6 |  | 2016-02-19 |  |  | Development of methodological materials and regulations for the establishment and operation of the centres | Each partner university will name 1 researcher to take part in this activity. | - | Administrators? Why?
2.2. |  |  | Arrangement of offices | Утверждение концепции с привлечением заинтересованных сторон, например, представителей рынка труда |  |  | 6 |  | 2016-03-14 |  |  | Arrangement of offices for the centres with equipment, software, staff etc. | Each PC country holds National Conference (P5, P10, P14, P17) for 3 days. 2 teachers from other universities of the country visit a conference. | +staff | Other institutions to be selected
2.3. |  |  | Documentation for planning and control | Разработка концепции нового подразделения университета | Seminars for other NIS partner universities for discussion and selection of operative plans of each Center, prepared during retraining of Centers' staff at EU universities. |  | 8 |  | 2016-03-28 |  |  | Development of documentation for planning and control for the centres | _____ academics from P7, P11, P13, P18 will participate in edit and preparation of the Final Concept.
2.4. |  |  | Hiring, training and probation of staff | Организация и внедрение нового подразделение в университете Academic Employment Committee | Preparation of Centres’ offices in each NIS university. Purchasing equipment for them (10 computers and 1 server for each RCC). Selection of 3 administrative staff for the each Regional coordination center. |  | 4 |  | 2016-04-14 |  |  | Hiring, training and probation of administrative staff for the centres
2.5. |  |  | Official opening and presentation of the centres | Organization of seminars at NMU | Organization of 2 seminars on management for retraining Centres' administrative staff for 8 NIS partner universities at NMU. |  | 4 |  | 2016-04-29 |  |  | Official opening and presentation of the Centers for PC Ministries and local authorities | 5 teachers from P1, P2, P4-P19 visit attend CUP within 7 days. CUP involves 2 administrators for holding the seminar.
2.6. |  |  | Validation of the centres by ministries | Official opening of the Centers | Official opening of the Centres with participation of the employment centers and regional administrations. Opening will take place with regional mas media. |  | 3 |  | 2016-04-30 |  |  | Validation of the centres by ministries | 3 teachers from P5-P7 will be trained during 1 month at the P2. 3 teachers from P10-P11 - at the P4. 3 teachers from P13-P14 - at the P3. 3 teachers from P17-P18 - at the P1. Each programme country involves 2 teachers for 15 days. | ?
2.7. |  |  | Annual meetings of the leaders of the centres |  |  |  | 3 |  | 2018-10-14 |  |  | Annual meetings of the leaders of the centres | 5 researchers from each partner university will take part in 12 courses development. | ?
3. | DEVELOPMENT | Information Systems for Support of the Centres |  | Information infrastructure of the Centres | In this phase of the project it will be created databases of senior and graduated students’ resumes after having tested students’ major skills and professional orientation. The next step will be creation of database of organizations, enterprises and firms, which are interested in students, graduated from participating universities is creating, placing of database structure on to the Centre’s web-site, providing convenient access to the data for registered users. |  |  | 2016-02-15 | 2018-10-14 |  |  | Development of information systems for Graduates Employment Centers
3.1. |  |  | Organisation of high-speed connection in the centres | Создание базы данных работодателей и выпускников ВУЗов | Creating database of senior and graduated students’ resumes, adding the database to the Centre’s web-site, provide convenient access to the data for registered users. Design of database of organizations, enterprises and firms, which are interested in students, graduated from participating NIS universities is creating, adding the structure of this database to the Centre’s web-site, provide convenient access to the data for registered users. Each Center will create database of the needs of regional employers in close cooperation with the regional authorities, employment centers, Chambers of commerce and industry and Unions of industrialists and entrepreneurs. |  | 3 |  | 2016-03-07 |  |  | Organization of high-speed connection of Centers | 2 administrators from each partner university will take part in regulatory documents preparation.
3.2. |  |  | Establishment of the centres’ webpages | Осуществление долгосрочного прогноза требований рынка труда |  |  | 4 |  | 2016-03-30 |  |  | Establishment of the Centres' webpage | At each partner university 1 manager and 1 administrator will be responsible for the interview for new candidates design and holding. | other
3.3. |  |  | Creation of database of employers and students | Semi-annual Employment Fairs | Regular meetings of potential employers with university administrations and students. Presentation of enterprises and firms, new university specialities and education standards, etc. |  | 30 |  | 2018-10-14 |  |  | Creating database of employers, senior and graduate students | 1 research and 1 administrator at each partner university will be responsible for the analysis of existing European literature in RNM, work out final list of demands. | other
3.4. |  |  | Formation of the monitoring system of jobs website |  |  |  | 8 |  | 2016-06-30 |  |  | Formation of the monitoring system of jobs website | 2 researchers from P10 and P14 creating developing plan for 3 days. | +
3.5. |  |  | Creation of the database’s analytical adjustments |  |  |  | 3 |  | 2017-10-14 |  |  | Creating of the database’s analytical adjustments for the rating of graduates and employers, and long-term forecasting of labor market requirements | 4 technician from P10 and P14 will be responsible for the OGNMA design. |  | other participants
4. |  | Establishment of Boards of Trustees and Alumni Associations |  | Boards of Trustees, University Senates | During the workpakage it will be established the Boards of Trustees, University Senates at each partner-country universities, making up resumes, seminar-presentation of up-to-date information on career areas and foreground assignment of students to different organizations. Internal PC universities’ regulations will be developed. 24 Boards of Trustees’ members will be participated at KLU meetings. 24 Senates’ members will be trained at UTN. |  |  | 2016-02-01 | 2018-03-21 |  |  | Foundation of Boards of Trustees (BT) and Alumni associations (AA)
4.1. |  |  | Foundation documents for BT and AA |  |  |  | 4 |  | 2016-02-28 |  |  | Development of organizational and methodological documents for the foundation of Boards of Trustees and alumni associations
4.2. |  |  | BT establishment at the universities |  |  |  | 8 |  | 2016-04-30 |  |  | Board of Trustees establishment at the universities
4.3. |  |  | Seminars for members of the Boards of Trustees |  |  |  | 2 |  | 2017-06-07 |  |  | Seminars for members of the Boards of Trustees
4.4. |  |  | Creation of alumni associations |  |  |  | 4 |  | 2016-06-30 |  |  | Creation of alumni associations at each PC university
4.5. |  |  | Organization of seminars for graduate students |  |  |  | 3 |  | 2016-07-07 |  |  | Organization of seminars for graduate students
4.6. |  |  | Local meetings with members of BT and AA |  |  |  | 3 |  | 2018-02-07 |  |  | Local meetings with members of Boards of Trustees and alumni associations
5 | EXPLOITATION | Internal University Regulations About “University-Employers” Cooperation |  | Alumni Associations |  |  |  | 2015-10-15 | 2018-10-14 |  |  | Development of internal university regulations about the cooperation between university and employers
5.1. |  |  | Creation of Guidelines regarding University-Employers Cooperation | Hiring, training and probation of Academic Employment Committee staff |  |  | 4 |  | 2015-11-15 |  |  | Creation of Guidelines for University-Employers Cooperation | 2 managers from P1, P2, P3, P6, P15, P18 universities will be responsible for the quarterly reports making. | other | Azerbaijan is missing
5.2. |  |  | Seminars and training of University Staff on University-Employers Cooperation Rules |  |  |  | 4 |  | 2015-12-15 |  |  | Seminars and training of University Staff on University-Employers Cooperation Rules | P4 is responsible for inviting the external expert which will provide review on the project quality and progress. Each year 1 administrator from P4 will perform this task. |  | Maby more funds?
5.3. |  |  | Implementation of Guidelines | Annual meetings of the leaders of the centres |  |  | 36 |  | 2018-10-14 |  |  | Practical implementation of rules | 1 administrator from P6, P11, P13, P18 (project coordinators in partner countries) and P5, P10, P17, P14 (National Committees in partner countries) will gather and analyze project documentation.
6. | DISSEMINATION | Dissemination of the Project |  |  | During the workpackage will be created web-site of the project with presentation of information in English and in Russian. SMSUH, CSU, NMU and SSU pass 5 local project meetings with participation of mass-media and representatives of regional and local administrations, employment centers, Chambers of commerce, Unions of industrialists. NIS universities will create free-libraries on the Centers which contains literature, collected during the project on directions of Centers' activity. KLU will pass seminars for all participants of project and educational societies of NIS. |  |  | 2016-03-14 | 2018-10-14 |  |  | Dissemination of the project
6.1. |  |  | Promotion of the project site | Project of the project web-site | Creation of the web-site of the Committee. Web-site will be updated during the project life and beyond and will be a main source of information about the Centre and its activities |  | 18 |  | 2016-05-14 |  |  | Promotion of the project site and the site to the database for employment in network | 1 researcher from P5 and P17 will be responsible for a requirements list creation. 4 technician from P5 and P17 will create website of the project. | -
6.2. |  |  | 6 local project meetings with mass-media | Mass-media events | local project meetings with participation of journalists in SMSUH, CSU, NMU and SSU. Promotion of European Higher Education Area, popularization of Alumni associations, Centres and a TEMPUS projects. Design of project logo and ordering of calendars, badges and stationery with the logotype. Publishing of brochures, posters, leaflets. |  | 6 |  | 2016-04-21 |  |  | 6 local project meetings with mass-media | 1 administrator from each partner university will be responsible for the timely uploading of all the materials and news within the project. | -
6.3. |  |  | Dissemination of project materials | Dissemination of project materials | Creation of Centres' free-libraries which contain literature, collected during the project on directions of Centers' activity (in RU,UA,MD,EN languages), will be arranged and storied in special depositories in the Centers for using by students and teacher. |  | 31 |  | 2018-10-14 |  |  | Dissemination of project materials between universities | 3 researchers from P2 and P3 will design dissemination materials. 1 administrator from each partner university would be responsible for spreading them. | other
6.4. |  |  | Publishing the bulletin of ReGEC Network | Publishing the bulletin of ReGEC Network |  |  | 3 |  | 2018-09-14 |  |  | Publishing the bulletin of Regional Graduates Employment Centers Network | 1 administrator from P1, P3, P2 will be responsible for meeting organization.
6.5. |  |  |  | Signing of cooperation agreements, establishing a communication network |  |  | 3 |  | 2018-10-14 |  |  | Result conference | 2 administrators from P5, P10, P14, P17 will organize events. 3 persons from each PC university will visit national dissimination conference in their countries (lasting 3 days), 2 persons from each European partner university attend these meetings also (P1 visits NMU, P2 visits BSU, P3 visits KazNU, P4 visits TSTU). | ???
Official opening and presentation of the centres
Establishment of the centres’ webpages
|  |  | Result conference | Drop-box | Experience exchange between educational societies of NIS and EU countries at NMU
6.6. |  |  | Publishing of international collaboration results | Drop-box |  |  | 3 |  | 2018-09-14 |  |  | Publishing of international collaboration results
7. | QUALITY PLAN | Quality control and monitoring |  |  | Level of coherence between work plan and actual results will be assessed by comparing the actually achieved results at the moment of the next assessment with those pointed out in the work plan. Expertise will carried our by the 2 external experts (subcontracted by NMU). They will evaluate the project results twice: in the middle of first and second project year. Finance audit of the project will be carried out by external audit company. |  |  | 2015-10-15 | 2018-10-14 |  |  | Quality control and monitoring of the project
7.1. |  |  | Annual evaluation of project quality by experts | Annual evaluation of project quality by Academic Employment Committee | Level of coherence between work plan and actual results will be assessed by comparing the actually achieved results at the moment of the next assessment with those pointed out in the work plan. Expertise will carried our by the 2 external experts (subcontracted by KLU). They will evaluate the project results twice: in the middle of first and second project year. Finance audit of the project will be carried out by external audit company. |  | 3 |  | 2018-09-14 |  |  | Annual evaluation of project quality by experts | 1 teacher from P1 visits P5 for 10 days to supervise students. 1 teacher from P1 visits P6 for 10 days to supervise students. 1 teacher from P2 visits P7 for 10 days to supervise students. 1 teacher from P3 visits P10 for 10 days to supervise students. 1 teacher from P4 visits P11 for 10 days to supervise students.
7.2. |  |  | Monthly analysis of project participants feedback | Semi-year analysis of project participants feedback | Quality control and monitoring will be carried out by comparison to the work plan, by analyzing the project participants questionnaires. Questionnaires are to be designed by all the consortium members and analyzed by the local coordinators. |  | 36 |  | 2018-10-14 |  |  | Monthly analysis of project participants feedback | Special Mob Strand: 2 students from P5-P7 visits P4 for 2 month in 2017. 2 students from P10-P11 visits P2 for 2 month in 2017. Travel Costs: 2 students from P13-P14 visits P1 for 2 month in 2017. 2 students from P17-P18 visits P3 for 2 month in 2017. Special Mob Strand: 2 students from P5-P7 visits P3 for 2 month in 2018. 2 students from P10-P11 visits P1 for 2 month in 2018. Travel Costs: 2 students from P13-P14 visits P2 for 2 month in 2018. 2 students from P17-P18 visits P4 for 2 month in 2018. P1-P4 has 60 working days for teachers and 10 working days for administrator.
7.3. |  |  | Implementation of TQM in the GEC’s activity | Assessment of the quality of education on the basis of the developed "quality standard of education" |  |  | 5 |  | 2016-06-14 |  |  | Implementation of TQM in the GEC’s activity
7.4. |  |  | On-line project estimation on the web-page | Drop-box |  |  | 34 |  | 2018-10-14 |  |  | On-line forum in the project web-page for project estimation
7.5. |  |  |  | Formation of the monitoring system of jobs website
8. | MANAGEMENT | Management of the Project |  |  | NMU will provide day-to-day coordination. University will create an International Management Group of realization the project. KLU and UTN will pass the meetings for strategic planning of project activities; execution of the project dissemination strategies; NIS IMG will implement of recommendations of the project quality control service; planning and realization of actions, aiming at sustainability of the results after the project end. Each NIS university will create Local Project Management Committee and prepare report of project progress. |  |  | 2015-10-15 | 2018-10-14 |  |  | Management system of the project
8.1. |  |  | General and Local Project Management Committees | Kick-off meeting |  |  | 36 |  | 2018-10-14 |  |  | General and Local Project Management Committees | 2 managers from P1, P2, P3, P4, P6, P10, P14, P17 will be responsible to perfom this activity. | - | no teachers
8.2. |  |  | Day-to-day management | Meetings of the management team/Webinars |  |  | 36 |  | 2018-10-14 |  |  | Day-to-day management | 2 researchers from P1-P6, P8-P19 will visits P7 for 3 days. 2 administrators from P7 will assure quality of the meeting.
8.3. |  |  | 6 semi-annual coordination meetings | Conflict issues resolving |  |  | 6 |  | 2018-09-14 |  |  | 6 semi-annual coordination meetings | 1 manager and 2 administrators from P1 hwill be responsible for the financial management. | + | +local ccordinators
8.4. |  |  | On-line control system of project implementation | Project management by project coordinator |  |  | 36 |  | 2018-10-14 |  |  | Placed on the web-site on-line system control of the project’s implementation. | One project manager an two administrators from P1, P6, P10, P14, P17 will perform day-to-day management tasks.
Project management by local coordinators

## Timeplan
|  |  |  | 2015 |  |  | 2016 | [11 empty] | 2017 | [11 empty] | 2018
|  |  |  | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
WP Type | Deliverable / Activity Ref. N° | Activities (as indicated in the LFM) | Dura- tion (weeks) | 2015 10: Month
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
PREP | 1.1. | Global Nature Management Association | 4 | Month 1: 1=X; Month 2: 3=X
PREP | 1.2. | Deep analytical review of state of PC education in the sphere of Global Nature Management | 6 | bar: Month 2 to Month 3
PREP | 1.3. | Deep review of state of European modern approaches to the education in the sphere of Global Nature Management | 6 | Month 2: 1=X; Month 3: 4=X; Month 4: 1=X
PREP | 1.4. | Bilateral agreements concerning the double-degree programme | 6 | Month 19: 3=X; Month 20: 1=X; Month 21: 1=X; Month 22: 1=X
PREP | 1.5. | International working groups of courses’ developers | 2 | Month 6: 2=X
PREP | 1.6. | List of selected tutors | 6
PREP | 1.7. | List of master students for pilot groups | 4 | bar: Month 13
DEV | 2.1. | Draft of the concept | 2 | Month 3: 1=X; Month 4: 1=X
DEV | 2.2. | National conference organized by PC Ministries | 4 | bar: Month 8
DEV | 2.3. | Final version of the concept, approved by National Ministries | 2 | bar: Month 13
DEV | 2.4. | Establishment of National Committees | 12 | bar: Month 8 to Month 9; Month 13 to Month 14
DEV | 2.5. | List of 6 new and 6 renewing courses on Global Nature Management | 12 | Month 7: 4=X; Month 8: 4=X; Month 9: 4=X
DEV | 2.6. | Tutor’s training at EU universities | 4 | bar: Month 14
DEV | 2.7. | Syllabi of the new and renewed courses | 46 | Month 10: 4=X; Month 11: 4=X; Month 12: 4=X; Month 13: 4=X; Month 14: 4=X; Month 15: 4=X; Month 20: 4=X; Month 21: 4=X; Month 26: 2X; Month 27: 2X; Month 28: 2X; Month 29: 2X; Month 30: 2X; Month 31: 4X
DEV | 2.8. | National Standards of Master curriculum on Global Nature Management for each PC | 9 | Month 24: 3=; Month 25: 4=; Month 26: 2=
DEV | 2.9. | New teaching materials and guidelines in Rational Nature Management Education | 15 | Month 11: 3X; Month 12: 3X; Month 13: 3X; Month 14: 3X; Month 15: 3=X
DEV | 3.1. | University regulations about the Centres | 5 | bar: Month 8 to Month 9
DEV | 3.2. | Assignment of the Center's staff | 4 | bar: Month 10
DEV | 3.3. | Launched Global Nature Management Centres | 6 | bar: Month 12 to Month 13; Month 15
DEV | 3.4. | International Society of Global Nature Management (ISGNM) | 112 | [6 empty] | 4=X | 4=X | 4=X | 4=X |  | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X |  | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X |  | 4=X
DEV | 3.5. | On-line Global Nature Management Academy (OGNMA) | 84 | [8 empty] | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 4=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X
QPLN | 4.1. | Quarterly reports on the progress and implementation of activities from Global Nature Management Association | 12 | Month 3: 1=X; Month 6: 1=X; Month 9: 1=X; Month 12: 1=X; Month 15: 1=X; Month 18: 1=X; Month 21: 1=X; Month 24: 1=X; Month 27: 1=X; Month 30: 1=X; Month 33: 1=X; Month 36: 1=X
QPLN | 4.2. | Annual consortium reviews of the project progress | 3 | Month 12: 1=X; Month 24: 1=X; Month 36: 1=X
QPLN | 4.3. | Project documentation keeping and analyzing | 36 | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X
QPLN | 4.4. | Stakeholders (students, teachers, enterprise) opinion polls. | 24 | Month 18: 2X; Month 19: 1X; Month 20: 1X; Month 21: 2X; Month 22: 2X; Month 24: 1X; Month 25: 1X; Month 26: 1X; Month 27: 1X; Month 28: 1X; Month 29: 1X; Month 30: 1X; Month 31: 1X; Month 32: 1X; Month 33: 2X; Month 34: 1X; Month 36: 4X
QPLN | 4.5. | Internal review of the Curriculum | 15 | Month 5: 4=X; Month 6: 2=X; Month 7: 1X; Month 8: 1X; Month 9: 1X; Month 10: 1X; Month 12: 1X; Month 13: 1X; Month 14: 1X; Month 24: 1X; Month 34: 1X
DISS | 5.1. | Project website | 40 |  |  |  | 4=X | 4=X | 2=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X
DISS | 5.2. | Dissemination of elaborated list of courses via project's, partner universities websites | 38 |  |  |  |  | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X | 1=X
DISS | 5.3. | Dissemination of quarterly bulletins, published materials | 26 | Month 3: 4=X; Month 6: 2=X; Month 9: 2=X; Month 12: 2=X; Month 15: 2=X; Month 18: 2=X; Month 21: 2=X; Month 24: 2=X; Month 27: 2=X; Month 30: 2=X; Month 33: 2=X; Month 36: 2=X
DISS | 5.4. | Annual conferences on ISGNM | 3 | Month 10: 1=X; Month 22: 1=X; Month 34: 1=X
DISS | 5.5. | Concluding conferences on results of projects | 3 | Month 36: 3=X
EXPL | 6.1. | Master students from pilot group trained at home universities | 60 | bar: Month 16 to Month 20; Month 24 to Month 32; Month 36
EXPL | 6.2. | Master students from pilot group trained in EU | 16 | bar: Month 21 to Month 22; Month 33 to Month 34
EXPL | 6.3. | International Assessment Committee | 4 | bar: Month 25
EXPL | 6.4. | Presentations of Master students’ researches. | 4 | bar: Month 33
EXPL | 6.5. | Alumni Association | 2 | Month 24: 4X; Month 25: 4X; Month 26: 2X; Month 27: 2X; Month 28: 2X; Month 29: 1X; Month 30: 1X; Month 31: 1X; Month 32: 1X; Month 33: 1X; Month 34: 1X; Month 35: 1X; Month 36: 1X
MNGT | 7.1. | Project Management Committee | 130 | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X
MNGT | 7.2. | Coordination meetings | 9 | Month 5: 1X; Month 10: 2=X; Month 16: 1X; Month 21: 2=X; Month 28: 1X; Month 34: 2=X
MNGT | 7.3. | Financial management | 130 | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X
MNGT | 7.4. | Day-to-day project coordination | 130 | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X | 2=X

## Partners
Partners
Acronym
Coordinator:
|  | P1 | NMU | NationalMining University of Ukraine | Ukraine
EU
|  | P2 | WTU | Wroclaw Technical University | Poland
|  | P3 | UKOLD | Koblenz-Landau University | Germany
|  | P4 | ASU | Aleksandras Stulginskis University | Lithuenia
|  | P5 | PU | Patras University | Greece
|  | P6 | WUS | World University Service | Austria
Ukraine
|  | P7 | DCEO | Dnipropetrovsk City Employment Organization
|  | P8 | DIA | Dnipropetrovsk Regional Investment Agency |  | подумать спросить у марины
|  | P9 | DESDR | Department for Education and Science of Dnipropetrovsk Region
|  | P10 | KNU | Khmelnitskiy National University
|  | P11 | SSU | Sumy State University
|  | P12 | CCSG | Chamber of commerce of Sumy Region
The Republic of Belarus
|  | P13 | BSU | Belarusian State University
|  | P14 | LSPCMCEC | Labour and social protection committee of Minsk City Executive Committee
|  | P15 | BrSU | Brest State University
|  | P16 | AUB | Association of European Business
|  | P17 | MEB | Ministry of Education (Belarus)
Armenia
|  | P18 | NPUA | National Polytechnic University of Armenia
|  | P19 | ASUE | Armenian state University of Economics
|  | P20 | YSULS | YerevanBrusovStateUniversity of Languages and Social Sciences
|  | P21 | EIF | Enterprise Incubator Foundation
|  | P22 | MEA | Ministry of Education of Armenia
[7 empty] | Participating org: | Ukraine: NMU Poland: WTU Germany: UKOLD Lithuenia: ASU Greece: PU Austria: WUS Ukraine: DCEO, DIA, DESDR, KNU, SSU, CCSG Republic of Belarus: BSU, LSPCMCEC, BrSU, AUB, MEB Armenia: NPUA, ASUE, YSULS, EIF, MEA | Ukraine: NMU (P1) Poland: WTU (P2) Germany: UKOLD (P3) Lithuenia: ASU (P4) Greece: PU (P5) Austria: WUS (P6) Ukraine: DCEO (P7), DIA (P8), DESDR (P9), KNU (P10), SSU (P11), CCSG (P12) Republic of Belarus: BSU (P13), LSPCMCEC (P14), BrSU (P15), AUB (P16), MEB (P17) Armenia: NPUA (P18), ASUE (P19), YSULS (P20), EIF (P21), MEA (P22)
[7 empty] | Languages: | English, Ukrainian, Azerbaijani, Kazakh, Uzbek